## Sheet1
Dark Order of Orthongonality and Object-Oriented Mastery (DOOOOM)
Progress
Deliverable
|  |  | January | [14 empty] | February | [19 empty] | March | [19 empty] | April
|  |  | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 31 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
PARTICIPANTS |  | TASK | January 13: WEEK1; January 20: WEEK2; January 27: WEEK3; February 3: WEEK4; February 10: WEEK5; February 17: WEEK6; February 24: WEEK7; March 3: WEEK8; March 10: WEEK9; March 17: WEEK10; March 24: WEEK12; April 31: WEEK13; April 5: WEEK14; April 10: WEEK15; April 15: WEEK16
| 1 | INTRODUCTION-- made up of:: DUE January 23rd, 2014
Essenam K. | 1.1 | A title page consisting of the class, semester, group name, group members, date | bar: January 16 to January 21; January 23
DOOOOM | 1.2 | Resumes of each group member | bar: January 13 to January 20; January 23
DOOOOM | 1.3 | Topic chosen | bar: January 13 to January 15; January 23
Essenam K. | 1.4 | WSD showing the group name, members and their assigned roll and the group coordinator | bar: January 13 to January 20; January 23
Zachery P. | 1.5 | A copy of the Contract Document signed by the group coordinator | bar: January 15; January 23
| 2 | Requirements Elicitation -- made up of:: Due February 13 th, 2014
Essenam K. | 2.1 | A title page consisting of the class, semester, Project title, group name, group members, date | bar: February 10 to February 11; February 13
Zachery P. | 2.2 | Problem statement expressed using "shall" statements | bar: January 27 to February 4; February 13
Essenam K. | 2.3 | RTM - the first 4 columns | bar: January 29 to February 6; February 13
Andrew F. | 2.4 | Updated WSD showing the group name, members and their assigned roll and the group coordinator | bar: January 27 to January 28; February 13
Obi A. | 2.5 | Gantt Chart showing allocation of task up to this point in the project | bar: February 6 to February 11; February 13
Philip R. | 2.6 | A dictionary explaining terms and computer jargons | bar: February 7 to February 11; February 13
Zachery P. | 2.7 | A rational for the topic chosen and the requirements and specification given in the problem statement. | bar: January 27 to January 28; February 13
| 3 | System Analysis and Design -- made up of:: Due February 27th, 2014
Essenam K. | 3.1 | A title page consisting of the class, semester, Project title, group name, group members, date | bar: February 27 to February 28; March 4
Zachery P. | 3.2 | A horizontal prototype of the software to be developed | bar: February 20 to February 28; March 4
Essenam K. | 3.3 | RTM - the first five columns and all other updates | bar: February 24 to February 28; March 4
Essenam K. & Zachery P. | 3.4 | Use cases and Interaction Diagrams - example as per given in class | bar: February 26 to February 28; March 4
Andrew F. | 3.5 | Function Point Cost Analysis | bar: February 24 to February 27; March 4
Philip R. | 3.6 | Database to be used | bar: February 26 to February 28; March 4
Andrew F. | 3.7 | Updated WSD showing the group name, members and their assigned roll and the group coordinator | bar: February 27 to February 28; March 4
Obi A. | 3.8 | Updated Gantt Chart showing allocation of task up to this point in the project | bar: February 26 to February 28; March 4
Philip R. | 3.9 | A dictionary explaing terms and computer jargons | bar: February 26 to February 28; March 4
Obi A. | 3.1 | A rational for the use cases, etc | bar: February 21 to February 27; March 4
| 4 | Document #4 -- Object Design -- made up of:: Due March 13th, 2014
Essenam K. | 4.1 | A title page consisting of the class, semester, Project title, group name, group mambers, date. | bar: March 10 to March 11; March 13
Zachery P. | 4.2 | Software architecture used | bar: March 10 to March 11; March 13
Essenam K. | 4.3 | RTM - the first five columns and all other updates | bar: March 7 to March 10; March 13
Essenam K. | 4.4 | A Category Interaction Diagram - example as per given in class | bar: March 4 to March 11; March 13
DOOOOM | 4.5 | Design of each object in the application i.e. the class interface | bar: March 5 to March 11; March 13
Andrew F. | 4.6 | Updated WSD showing the group name, members and their assigned roll and group coordinator. | bar: March 7 to March 11; March 13
Obi A. | 4.7 | Updated Gantt Chart showing allocation of task up to this point in the project | bar: March 7 to March 11; March 13
Philip R. | 4.8 | A dictionary explaing terms and computer jargons | bar: March 10 to March 11; March 13
Zachery P. | 4.9 | A rational for the objects in the application, software architecture, etc. | bar: March 4 to March 11; March 13
| 5 | Document #5 -- Rationale for the entire project including design -- made up of:: Due March 25th, 2014
Essenam K. | 5.1 | A title page consisting of the class, semester, Project title, group name, group members, date | bar: March 20 to March 21; March 25
DOOOOM | 5.2 | Take all of your rationale so far and put it together as one document | bar: March 14 to March 21; March 25
Essenam K. | 5.3 | RTM - the first five columns and all other updates | bar: March 19 to March 21; March 25
Andrew F. | 5.4 | Updated WSD showing the group name, members and their assigned roll and group coordinator | bar: March 20 to March 21; March 25
Obi A. | 5.5 | Updated Gantt Chart showing allocation of task up to this point in the project | bar: March 20 to March 21; March 25
Philip R. | 5.6 | A dictionary explaing terms and computer jargons | bar: March 20 to March 21; March 25
| 6 | Document #6 -- Test document and code so far -- made up of:: Due April 8th, 2014
Essenam K. | 6.1 | A title page consisting of the class, semester, Project title, group name, group members, date | bar: April 5 to April 6; April 8
Essenam K. | 6.2 | RTM - the first five columns and all other updates | bar: April 4 to April 5; April 8
DOOOOM | 6.3 | The source code and executable code on disk that you have done so far. | bar: April 31 to April 5; April 8
DOOOOM | 6.4 | Test cases used to test your software - format as per discuss in class i.e. type of tests used and how many | bar: April 1 to April 6; April 8
Philip R. | 6.5 | COCOMO | bar: April 4 to April 6; April 8
Andrew F. | 6.6 | Updated WSD showing the group name, members and their assigned roll and group coordinator | bar: April 4 to April 6; April 8
Obi A. | 6.7 | Updated Gantt Chart showing allocation of task up to this point in the project | bar: April 5 to April 6; April 8
Philip R. | 6.8 | A dictionary explaing terms and computer jargons | bar: April 4 to April 6; April 8
DOOOOM | 6.9 | A rational for tests cases and type used, etc | bar: April 1 to April 6; April 8