## Sheet1
Dark Order of Orthongonality and Object-Oriented Mastery (DOOOOM)
Progress
Deliverable
|  |  | January | [14 empty] | February | [19 empty] | March | [20 empty] | April
|  |  | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 31 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 28
PARTICIPANTS |  | TASK | January 13: WEEK1; January 20: WEEK2; January 27: WEEK3; February 3: WEEK4; February 10: WEEK5; February 17: WEEK6; February 24: WEEK7; March 3: WEEK8; March 10: WEEK9; March 17: WEEK10; March 24: WEEK12; March 31: WEEK13; April 7: WEEK14; April 14: WEEK15; April 21: WEEK16
| 1 | INTRODUCTION--DUE Jan 23rd, 2014
Essenam K. | 1.1 | A title page | bar: January 16 to January 21; January 23
DOOOOM | 1.2 | Resumes of each group member | bar: January 13 to January 20; January 23
DOOOOM | 1.3 | Topic chosen | bar: January 13 to January 15; January 23
Essenam K. | 1.4 | Work Schedule Diagram | bar: January 13 to January 20; January 23
Zachery P. | 1.5 | A signed copy of the Contract Document | bar: January 15; January 23
| 2 | Requirements Elicitation Due Feb 13th, 2014
Essenam K. | 2.1 | A title page | bar: February 10 to February 11; February 13
Zachery P. | 2.2 | Problem statement expressed in "shall" statements | bar: January 27 to February 4; February 13
Essenam K. | 2.3 | RTM - the first 4 columns | bar: January 29 to February 6; February 13
Andrew F. | 2.4 | Work Schedule Diagram | bar: January 27 to January 28; February 13
Obi A. | 2.5 | Gantt Chart showing | bar: February 6 to February 11; February 13
Philip R. | 2.6 | A dictionary explaing terms and computer jargons | bar: February 7 to February 11; February 13
Zachery P. | 2.7 | A rational for the topic chosen and the requirements | bar: January 27 to January 28; February 13
| 3 | System Analysis and Design Due Feb 27th, 2014
Essenam K. | 3.1 | A title page | bar: February 27 to February 28; March 4
Zachery P. | 3.2 | A horizontal prototype of the software | bar: February 20 to February 28; March 4
Essenam K. | 3.3 | RTM - the first five columns and all other updates | bar: February 24 to February 28; March 4
E. K. & Z. P. | 3.4 | Use cases and Interaction Diagrams | bar: February 26 to February 28; March 4
Andrew F. | 3.5 | Function Point Cost Analysis | bar: February 24 to February 27; March 4
Philip R. | 3.6 | Database to be used | bar: February 26 to February 28; March 4
Andrew F. | 3.7 | Work Schedule Diagram | bar: February 27 to February 28; March 4
Obi A. | 3.8 | Updated Gantt Chart | bar: February 26 to February 28; March 4
Philip R. | 3.9 | A dictionary explaing terms and computer jargons | bar: February 26 to February 28; March 4
Obi A. | 3.1 | A rational for the use cases, etc | bar: February 21 to February 27; March 4
| 4 | Object Design Due March 13th, 2014
Essenam K. | 4.1 | A title page | bar: March 10 to March 11; March 13
Zachery P. | 4.2 | Software architecture used | bar: March 10 to March 11; March 13
Essenam K. | 4.3 | RTM - the first five columns and all other updates | bar: March 7 to March 10; March 13
Essenam K. | 4.4 | A Category Interaction Diagram | bar: March 4 to March 11; March 13
DOOOOM | 4.5 | Design of each object in the application | bar: March 5 to March 11; March 13
Andrew F. | 4.6 | Work Schedule Diagram | bar: March 7 to March 11; March 13
Obi A. | 4.7 | Updated Gantt Chart | bar: March 7 to March 11; March 13
Philip R. | 4.8 | A dictionary explaing terms and computer jargons | bar: March 10 to March 11; March 13
Zachery P. | 4.9 | A rational for the objects | bar: March 4 to March 11; March 13
| 5 | Rationale Due March 25th, 2014
Essenam K. | 5.1 | A title page | bar: March 20 to March 21; March 25
DOOOOM | 5.2 | All of your rationale so far | bar: March 14 to March 21; March 25
Essenam K. | 5.3 | RTM - the first five columns and all other updates | bar: March 19 to March 21; March 25
Andrew F. | 5.4 | Work Schedule Diagram | bar: March 20 to March 21; March 25
Obi A. | 5.5 | Updated Gantt Chart | bar: March 20 to March 21; March 25
Philip R. | 5.6 | A dictionary explaing terms and computer jargons | bar: March 20 to March 21; March 25
| 6 | Test document Due April 8th, 2014
Essenam K. | 6.1 | A title page | bar: April 8
Essenam K. | 6.2 | RTM - the first five columns and all other updates | bar: April 4; April 8
DOOOOM | 6.3 | The source code and executable code on disk. | bar: March 31 to April 4; April 8
DOOOOM | 6.4 | Test cases used to test your software | bar: April 1 to April 4; April 8
Philip R. | 6.5 | COCOMO | bar: April 4; April 8
Andrew F. | 6.6 | Work Schedule Diagram | bar: April 4; April 8
Obi A. | 6.7 | Updated Gantt Chart | bar: April 8
Philip R. | 6.8 | A dictionary explaing terms and computer jargons | bar: April 4; April 8
Zachery P. | 6.9 | A rational for tests cases and type used, etc | bar: April 1 to April 4; April 8
| 7 | Final document Due April 28th, 2014
Essenam K. | 7.1 | A title page | bar: April 23 to April 24; April 28
Essenam K. | 7.2 | Table of Contents | bar: April 23 to April 24; April 28
DOOOOM | 7.3 | Revised documents | bar: April 17 to April 21; April 28
DOOOOM | 7.3.1 | Introduction | bar: April 17 to April 23; April 28
DOOOOM | 7.3.2 | Requirements Elicitation | bar: April 18 to April 23; April 28
DOOOOM | 7.3.3 | System Analysis and Design | bar: April 17 to April 23; April 28
DOOOOM | 7.3.4 | Object Design | bar: April 17 to April 23; April 28
DOOOOM | 7.3.5 | Test document | bar: April 15 to April 23; April 28
Andrew F. | 7.4 | FPC and COCOMO | bar: April 21 to April 23; April 28
DOOOOM | 7.5 | Prototype | bar: April 17 to April 24; April 28
DOOOOM | 7.6 | Project legacy | bar: April 23 to April 24; April 28
Andrew F. | 7.7 | Work Schedule Diagram | bar: April 23 to April 24; April 28
Obi A. | 7.8 | Updated Gantt Chart | bar: April 18 to April 23; April 28
Philip R. | 7.9 | A dictionary explaing terms and computer jargons | bar: April 23 to April 24; April 28
DOOOOM | 8 | Group members resume | bar: April 24; April 28
DOOOOM | 8.1 | User Guide | bar: April 15 to April 24; April 28
Essenam K. | 8.2 | A print out of all source code | bar: April 23 to April 24; April 28
Essenam K. | 8.3 | A flash drive containing executables e.t.c | bar: April 23 to April 24; April 28